## Slide 1: Set Up, Implementation and Assessment of NKM Projects
School of Nuclear Knowledge Management
3-7 September 2012
Trieste, Italy
Presentation by Ed Boyles

## Slide 2: Contents
Choice of NKM project
NKM project prerequisites
Implementation aspects
Key success factors
NKM programmes
Review of KM projects
Questions

## Slide 3: Selecting NKM Projects
Reactive
Legislation
Customer/stakeholder requirements
Proactive
Benchmarking studies & competitor analysis
KM audit/maturity models
Business issues
Business improvement initiatives
Understand your DRIVERS!!!! & Ultimate BENEFITS
Notes: Sometimes KM projects are ‘forced’ on organizations due to changes in legislation or from other external sources. These are reactive implementations
More usually the organization selects projects in a proactive way. This can be done using any of the above methods.
A third possibility is by ‘accident’. Some projects are undertaken where the initial intention is not KM related. Later, aspects of the project are classified KM retrospectively

## Slide 4
There’s Room For Improvement
75% of IT projects are behind schedule
55% of all IT projects exceed their initial budget
37% failed to meet project requirements
And some, after huge investments of time and money, are simply never complete…….
Notes: Source – Bull report for IT projects in UK (1998) and the Standish Group
No specific reference material for KM projects – but would suggest that the same failure rates apply

## Slide 5: Project Prerequisites 1
Does the project align with organisational needs?
Is the purpose of the project clearly defined?
Are the benefits understood and well communicated?
Is there top level management support/commitment?
Is there a senior management sponsor?
Is a project manager assigned?
Are resources made available?
Is there sufficient ‘know how’ in the project team?
Before the project begins:
Notes: Experience suggests that all these prerequisites should be in place for a successful project – these are the key success factors
Resources include both human resource, equipment/technology and financial
Project team ‘know – how’ means
an understanding of what KM is,
an understanding of the business issues, and
Credibility in the project technical area
A recent study by Young/Jordan suggest that top management support is the most important critical success factor for project success.
(see International Journal of Project Management , Vol 26, Issue 7)

## Slide 6: Project Prerequisites 2
Is knowledge sharing encouraged?
Is knowledge regarded as critical to individual and organizational success?
Is innovation encouraged?
Is self/organizational learning and development the norm?
For sustained benefit, cultural issues need to be addressed:
If the above are not in place, the project may also need to be treated as part of a cultural change initiative
Notes: Specific issues and advice related to KM and culture is the subject of a separate presentation

## Slide 7: Project Scope
Is there a need for a pilot project?
Is full implementation intended?
Local or Company wide?
Is a KM “programme” required – see later
Other considerations:
Notes: Sometimes a pilot is a good idea for testing complex or new ideas before full implementation. This helps to reduce implementation risk.
For large organizations involving several locations bullet 3 is important
A KM programme is a number of separate KM projects run in parallel

## Slide 8: Typical Implementation Methodology (Including a Pilot Project Phase)
Communication
Presentations/Workshops
Stakeholder management
Phase 1 - Orientation
Familiarisation
Planning (inc. BP?)
Sponsorship
Phase 2 –Diagnosis
Benchmarking audit
Fit to organizational drivers,
Select pilot
Update plan
Phase 3 –Pilot Implementation
Develop initial roadmap
Select tools/methodologies
Run project pilot
Lessons Learned from pilot
Time
Phase 4 Full implementation
Detailed plan
Roll out to other relevant areas
Working smarter
Collaboration &
Sharing
Improved teamwork
Increased learning
Making better decisions
Embedding behaviours
KM Drivers
~1Month
~3 to 6 Months
~ 3 to 6 Months

## Slide 9: Case Study – Example Project

## Slide 10: Example KM Project Structure
Project Sponsor
Project Manager
Phase Review Team or Steering Group
Senior Manager 1
IT Development Team
Database Developer
Web Developer
Process Development Team
Business process analyst
QA
support engineer
Implementation Team
Business Team members
(various disciplines/skills)
Senior Manager 2
Senior Manager 3
Senior Manager 4
Notes: The IT development team and process development team typicaly come from the IT department & QA department respectively (but this need not be the case)
The Implementation team should come from the area(s) of the organization the project is to be implemented
A phase review team is an independent team of senior managers who scrutinize the project and ensure alignment with the business. They meet on a regular basis (perhaps 3 or 4 times during the duration of the project.

## Slide 11: Full Implementation Strategy
Pilot outcome very important
Receptiveness of organisation to cultural change is very important
Options for full implementation:
  “Wide & thin” (limited functionality but across a large number of units)
  “Narrow and thick” (rich functionality but across one or two business units)
  “Hybrid” (a portfolio of initiatives)
Notes: Hybrid option is essentially the same as a KM programme as defined later

## Slide 12: KM Projects - Key Learning Points
KM methodologies and technologies work!
KM projects work best when they are focussed on real business issues
KM has many aspects and techniques. Selection of the best approach is very important
Much can be done without massive IT expenditure
Savings & benefits are very difficult to quantify - hidden by other initiatives ( e.g. restructuring, change in external conditions, new IT systems)
Ensure adequate resources are allocated
Beware of time overruns!

## Slide 13
A KM Project
Resources
A KM Project
A KM Project
A KM Project
A KM Project
A KM Project
A KM Project
A KM Project
Cross Project
Links
Prioritisation
Performance
Management
KM Programme Management
Notes: KM programme management is running a portfolio of KM projects –usually in parallel
All need prioritizing and need to be carefully monitored to ensure satisfactory performance (performance management)
Cross project links refer to the ability to understand how individual projects interact.

## Slide 14: KM Programmes vs KM Projects
KM Project
Has a defined start and finish date.
Focus is more on delivering immediate objectives
Simpler to set up and manage
Projects are ‘ring fenced’.
Usually have a narrow view
KM Programme
Contain many projects
Can be merged with management systems to drive continuous improvement
Have to address multiple initiatives
Culture & change are very important
More complex interface with the strategy
Less well defined end date.
Focus is on delivering benefits and require action even when projects have ended.
Every programme must lead to business benefit
Notes: Programme risk management starts before projects start and continues after the last project has closed (e.g. operations might not use the deliverables.)

## Slide 15
The Value Path
KM Projects create deliverables. Programmes combine deliverables to create capabilities. The organisation utilizes the capabilities and gains BENEFITS
BENEFITS
Capabilities
Programmes
Deliverables
Project 1
Project 2
Project 3

## Slide 16: Review of KM Projects
Project Reviews or ‘post-mortems’ are examinations at the end of a project to determine if:
the objectives of the project were achieved
the intended benefits were realised
lessons can be learned for future projects
Notes: How do we ascertain if a KM project was a success?
KM projects are no different to any other project in this regard

## Slide 17: Assessment Techniques
Objective checklist
Questionnaires to determine perception of project success
Pre and post project KPIs

## Slide 18: Objective Checklist
KM objective 1
KM objective 2
KM objective 3
KM objective 4
KM objective 5
KM objective 6
√
√
√
√
√
√
We’ve achieved our objectives and…..
Completed on time and within budget so the project must be a success!!
Notes: Were the project objectives established at the start of the project realised?
Were they achieved within time & budget?
One measure of success.
If only some of the objectives were achieved then the project was a “partial” success.

## Slide 19: Questionnaires or Critiques
KM Project Questionnaire
In my opinion this project was a great success!!
Notes: Asking participants, in the form of a questionnaire, is a valuable method of receiving feedback on the success of the project.
Although only a qualitative measure, it is very important especially for the success of future initiatives.
Make sure results of successes are well communicated.

## Slide 20: Using KPIs
Key Performance Indicator 1
Time
KM Project starts
Performance
What a great project!!
Notes: KPIs must be established before the project begins.
The choice of KPIs depend on the type of project undertaken and should relate to the benefits sought.

## Slide 21: Summary
There are key success factors to consider at the outset when selecting and planning NKM projects
Certain pre-requisites must be in place to ensure success
Managing NKM projects is very similar to managing ‘change management projects’
Portfolio management or programme management is used to run multiple KM initiatives
Different techniques can be used to determine success of NKM projects

## Slide 22: Thank You For Your Attention Questions ?